## estimate
[8 empty] | 800 | 750
Product Name |  | Intercompany solution for SAP Business One |  |  |  | Customer Name: acme, Partner Name: XYZ
Product Version |  | 2 |  |  |  | Estimated total implementation effort
[6 empty] | Environment | in HOUR
Total no. of companies = |  | 3 | (HO + Branches + Consolidaiton) |  |  | Testing environment setup + UAT + Project mgt & communication | 97.85
Total no. of consolidation companies = |  | 1 |  | 97.85 |  | Production environment setup | 34.85
[6 empty] | Total | 132.7
Sl. No. | Module | Required | Training/Additional hours | Module wise hours (summary view)
1 | Base Product Setup | Y | 4 | 18.8 |  | Notes: Business one users : 20 Assumptions: Custom Company template config: 2 Global data Authorizaiton: 20 user per company
2 | Master Data replication | Y | 1 | 1
3 | Allocation | Y | 2 | 6.9
4 | InterCompany Trade | Y | 1.5 | 1.8
5 | Centralized Payments | Y | 0.5 | 0.5
6 | Consolidation | Y | 2 | 12.5
7 | InterCompany Service Management | Y | 0.5 | 0.5
8 | Consolidated credit limit check | Y | 0.5 | 1.4
9 | UDF/UDT replication | Y | 0.5 | 3.95
10 | Intercompany Reports | Y | 1.5 | 1.5
11 | Trouble shooting training | Y | 1 | 1
12 | UAT | Y | 24 | 24
13 | Project management and communication | Y | 24 | 24
Sl. No. | Activity/Category | Functional Area | Activity Description | Responsibility | Fixed Hours | Hours per Company | Total Hours | Excel Template
1 | Installation | Mandatory | Add-on Installation in each Partner Company | Implementation Consultant |  | 0.3 | 0.9
2 | Master Setup | Mandatory | login with B1i user once to initialize the user | Implementation Consultant |  | 0.1 | 0.3
3 | Installation | Mandatory | Intercompany Scenario Installer | Implementation Consultant | 1 | NA | 1
4 | Landscape Setup | Mandatory | Setup custom company template configuration | Implementation Consultant | 2 | NA | 2
5 | Landscape Setup | Mandatory | Setup InterCompany Landscape | Implementation Consultant | 0.5 | NA | 0.5 | Y
6 | Landscape Setup | Mandatory | Deploy Landscape and Initialize Data to B1 Companies | Implementation Consultant | 0.5 | NA | 0.5
7 | Master Setup | Mandatory | Currency Setup across SBO Companies. Prepare a consolidated list of currencies across partner companies. This master is common to all companies | Customer |  | NA | 0 | Y
8 | Master Setup | InterCompany Trade | Create a superset of master records for all key-mapped masters based on the applied company template: a. Payment Terms b. Freight c. Length & Width UOM d. Weight UOM e. Item Group f. Price List g. Currency h. Business Partner Group i. Manufacturer j. Discount Groups k. PackageTypes l. Unit of Measurement Groups m. Units of Measurement | Customer |  | NA | 0 | Y
9 | Landscape Setup | InterCompany Trade | Verify Key Mapping Master Record in each company(All Key Mapping Masters should have same no of records across branch companies) | Implementation Consultant |  | 0.5 | 1.5
10 | Landscape Setup | InterCompany Trade | Key Mapping | Implementation Consultant |  | 0.25 | 0.75 | Y
11 | Master Setup | Mandatory | Define General Settings (in SBO Companies) | Implementation Consultant |  | 0.3 | 0.9 | Y
12 | Master Setup | Mandatory | Update User Setup (in SBO Companies) | Implementation Consultant |  | 0.3 | 0.9 | Y
13 | Master Setup | Mandatory | Define Intercompany General Settings | Implementation Consultant |  | 0.3 | 0.9 | Y
14 | Master Setup | Mandatory | Define Intercompany Alerts Administration (in SBO Companies) | Implementation Consultant |  | 0.3 | 0.9 | Y
15 | Master Setup | Mandatory | Define B1i Setup (in SBO Companies) | Implementation Consultant |  | 0.3 | 0.9 | Y
16 | Master Setup | Mandatory | Define Messaging Setup (in SBO Companies) | Implementation Consultant |  | 0.3 | 0.6 | Y
17 | Master Setup | Mandatory | Define Global Data Authorization for average 20 users | Implementation Consultant |  | 1 | 2 | Y
18 | Master Setup | Mandatory | Define Global Data distribution for average 1 template per object | Implementation Consultant | 0.25 | 0 | 0.25 | Y
19 | Master Setup | Mandatory | Assign Global Data distribution template to global masters via DTW tool | Customer |  | 0 | 0
20 | Master Setup | Mandatory | Define Current Exchange Rates in Each Partner Company | Customer |  | 0 | 0
21 | Master Setup | InterCompany Trade | Define Control Accounts for each IC Partner Vendor / Customer Pair in the Chart of Accounts | Customer |  | NA | 0 | Y
22 | Master Setup | InterCompany Trade | Define Vendor / Customer Pair for each Partner Company | Implementation Consultant |  | 0.15 | 0.3 | Y
23 | Master Setup | InterCompany Trade | Item Master Setup for Common Items | Customer |  | NA | 0
24 | Master Setup | InterCompany Trade | Business Partner Setup for Common Partners | Customer |  | NA | 0
25 | Master Setup | G/L Allocation / Centralized Payments | Define Due to & Due from Accounts for each Partner Company in the Chart of Accounts | Customer |  | NA | 0
26 | Master Setup | G/L Allocation / Centralized Payments | Branch Accounts Setup | Implementation Consultant |  | 0.3 | 0.6 | Y
27 | Master Setup | Allocation | Define Default Expense Account in the Chart of Accounts | Customer |  | NA | 0
28 | Master Setup | Allocation | Define Default Income Account in the Chart of Accounts | Customer |  | NA | 0
29 | Master Setup | Allocation | Define Rounding Account in the Chart of Accounts | Customer |  | NA | 0
30 | Master Setup | Allocation | Default Accounts Setup | Implementation Consultant |  | 0.15 | 0.3 | Y
31 | Master Setup | Allocation | Map Accounts for Default P&L categories | Implementation Consultant |  | 1 | 2 | Y
32 | Master Setup | Allocation | Map Accounts for Default Balance Sheet categories | Implementation Consultant |  | 1 | 2 | Y
33 | Master Setup | Service Management | Ensure that Inventory Setup in General Settings is Identical | Customer |  | NA | 0
34 | Consolidation Setup | Consolidation | Prepare Consolidation COA | Customer |  | NA | 0
35 | Consolidation Setup | Consolidation | Setup Consolidation Company | Customer |  | NA | 0
36 | Consolidation Setup | Consolidation | Consolidation Activities: 1. Define Exchange Rate Gains / Losses Account in the Chart of Accounts 2. Define Residual Account in the Chart of Accounts 3. Define Currency Exchange Rates for Consolidation | Customer |  | NA | 0
37 | Consolidation Setup | Consolidation | Consolidation Account Setup | Implementation Consultant |  | 0.15 | 0.15 | Y
38 | Consolidation Setup | Consolidation | Define Account Consolidation Translation Method in Branch Companies | Implementation Consultant |  | 1.15 | 3.45 | Y
39 | Consolidation Setup | Consolidation | Import Consolidation COA to each partner company | Implementation Consultant |  | 0.3 | 0.9
40 | Consolidation Setup | Consolidation | Account Mapping for Consolidation (to be done in each partner company) | Implementation Consultant |  | 2 | 6 | Y
41 | Consolidated credit limit check | CreditLimits | Define credit limit check in all branch companies | Implementation Consultant |  | 0.3 | 0.9
42 | Consolidated credit limit check | CreditLimits | Define consolidated credit limits for BP in all branch companies | Customer |  | NA | 0
43 | UDF/UDT replication | UDF/UDT | Ensure UDFs/UDTs definition is same across branch companies | Customer |  | NA | 0
44 | UDF/UDT replication | UDF/UDT | custom replication setup for UDF/UDTs | Implementation Consultant |  | 1.15 | 3.45
Assumptions:
This estimate assumes that the SAP Business One has already been setup for transactions, including all setups and master data creation
This estimate assumes that all excel templates indicated in column I are prepopulated by the Customer before the implementation activity is undertaken by Walldorf solution
This estimate assumes that for UDF/UDT replication feature on an average 4 custom UDFs per object and 5 UDTs need to be replicated .
This esimated effort is only for one time setup either on test server or live server, Any activity beyond assumptions or notes in this document will be charged extra.